## April 1
Author: Vivek Ganesan |  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Pac Man 4 player |  |  |  |  | Logan Scott | lscott34@uic.edu
Week Of: 4/15 |  |  |  |  | Paul Morgan | pmorga3@uic.edu
[5 empty] | Vivek Ganesan | vganes7@uic.edu
[5 empty] | Ibrahim Ayoob | iayoob2@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Build the pac men that will travel around the maze. |  | Logan Scott | Built the pac men | Implement Game Scoring Logic/Server Client
Create dots, ghosts, and algorithm for ghost travel. |  | Ibrahim Ayoob | Build the Ghost AI | Create algorithm for ghost travel
Build the Server/Client GUI. |  | Paul Morgan | Built basic framework for client/server model | Extra Add-Ons
Note any issues, update design doc |  | Vivek Ganesan | Managed and delegated activities | Figure out any issues and add them to design doc